## SUMMARY
SUMMARY - COLLEGE & DAC EMERGENCY FACILITIES MAINTENANCE & REPAIR NEEDS
| Location | Amount
| BCC | 4500
| COA | 390000
| LANEY | 3378250
| MERRITT | 258150
| DAC | 1800
| Grand Total: | 4032700
Updated: October 22, 2013

## BCC
ALL ITEMS ON THE LIST ARE COMPLETE
2013-10-21
BERKELEY CITY COLLEGE
PRIORITY | STATUS | College | Building /Area | M= Maint. R = Repair | Description | Justification | ENGINEERING COST ESTIMATES | DGS Comments
C | C | BCC | Various | M | New Security Cameras need to be connected to the security monitors. | Without functional cameras it is hard to track safety, vandalism and theft. | 4500 | COMPLETED
[5 empty] | BCC TOTALS: |  | 4500

## COA
Ranked by Order of Priority
2013-10-21
COLLEGE OF ALAMEDA
PRIORITY | RISK MANAGEMENT RANKING | STATUS | College | Building /Area | M= Maint. R = Repair | Description | Justification / Comments | ENGINEERING COST ESTIMATES | RISK MANAGEMENT Comments | DGS Comments
1 | 1 | IN- PROGRESS Construction Planning Phase | COA | Entire campus | M | Potholes in the streets & pathways are not level | Trip and fall hazard | 275000 | Recommend that temporary asphalt patched be applied until construction documents are created and repairs are funded and completed | Proposals for Design engineers to prepare construction documents are currently being created. Once Architect/Engineer is selected Next steps will be: Board approval, Contract Document preparation, DSA review and approval Bidding, then Construction. Requistion for asphatt to repair potholes.
C | C | Complete | COA | Student Center/A Building | R | Replace broken windows | Hazard | 5000 |  | COMPLETED
C | C | Complete | COA | Library | R | Water leak under the Library | If repair does not happen, the sewage bill will continue to rise. The damage that the leak is causing will continue to escalate. | 110000 |  | COMPLETED
[6 empty] | COA TOTALS: |  | 390000

## LANEY
Ranked by Order of Priority (1st, 2nd, 3rd, etc)
10/22/2013 revised by Laney Facilities Planning Committee 4 nov 2013
LANEY COLLEGE
PRIORITY | RISK MANAGEMENT RANKING | STATUS | College | Building /Area | M= Maint. R = Repair | Description | Justification / Comments | ENGINEERING COST ESTIMATES | RISK MANAGEMENT Comments | DGS Comments
4 | 2 | PARTIALLY COMPLETE | Laney | Bistro Air handlers | R | Negative air pressure in Bistro. Problems with makeup air system. | Life & Safety Issue | 100000 | No comment | Partially Completed. Will be revisited.
NR in progress--no ranking needed per VC General Services | 1 | IN-PROGRESS Design Engineer Selection | Laney | Lower "A" & "B" buildings, multiple sites. | R | Major water leaks. At least eight leaks into labs with electrical hazards, high voltage hazards and damage to equipment and machinery. | Life & Safety Issue | 225000 | Find cost effective solution to patch leaks until work is awarded and repairs are funded/completed. | Proposals for Design engineers to prepare construction documents have been received and are currently being evaluated. Next steps Design repairs and put documents out for DSA review and Bid for construction. RFP going to the Board of Trustees on 9/24/13.
NR in progress--no ranking needed per VC General Services | 1 | IN-PROGRES Architect Selection | Laney | Breezeways and walkways throughout campus | R | Rough, uneven pavement and walkways across campus. Severe trip hazards from sinking drains and uneven pavement. 40-year old drain pipes across campus are rotting causing leaks and potential leaks | Life & Safety Issue | 1200000 | Identify hazards with yellow hazard warning paint and apply temporary asphalt patches until project is funded and work completed | Project Architect has been selected and is being submitted to the Board for approval at the next Board meeting. After approval Design and specifications for repair will be made. Project will the be submitted to DSA for approval. Then Bid and constructed. Item going to the Board on 9/24/13.
11 | 1 | IN- PROGRESS PRIIORITY | Laney | Chemistry Labs - A235B,A277 & A279 | M | Purchase and install Class D (metal) fire extinguishers | Life & Safety Issues. Lab house and use pyrophoric metals such as sodium, lithium, and other active agents such as sodium borohydride. | 500 | Maintenance - In Process Assigned High Priority | Maintenance - In Process Assigned High Priority
NR in progress--no ranking needed per VC General Services | 2 | IN-PROGRESS Design Engineer Selection | Laney | Biology Lab - Prep Area | M | Cold rooms in lab prep area. Mold always returns after cleaning and is quite extreme. | Life & Safety Issue. There are massive amounts of mold blowing through the ventilation in the cold rooms and causing problems for the items in storage (like the cadaver) and the people who work in and around those areas. | 75000 | Mold return is due to poor housekeeping and spillage as metal room does not have a food source for mold. Recommend procedures to increase cleaniness | Proposals for Design engineers to prepare construction documents are currently being created. Once the Architect/Engineer is selected. Next steps will be: Board approval, Contract Document preparation, DSA review and approval Bidding, then Construction. 3-4 rooms for cadavers
10 | 1 | PENDING Procurment HR/Risk Action Item | Laney | Chemistry Lab - A278 | M | Replace and install Corrosive material (blue) storage cabinet and add additional corrosive cabinet and vent both to the ventilation system. | Life & Safety Issues Acid spills. | 5000 | OSHA requirement | HR/Risk to define and procure cabinets to be installed and vented by contractors Procureemnt to include cabinets and installation.
8 | 1 | IN-PROGRESS Design Engineer Selection | Laney | Chemistry Lab - A235B, A278 & A279 | A235B, A278 & A279 | Ventilation of flammable storage cabinets doesn’t work. | Life & Safety Issues. Original installation has never worked correctly. | 6000 | OSHA requirement | Proposals for Design engineers to prepare construction documents are currently being created. Once Architect/Engineer is selected next steps: Board approval, Contract Document preparation, DSA review and approval Bidding, then Construction.
9 | 1 | IN-PROGRESS Design Engineer Selection | Laney | G-100 | R | Electrical wiring pull access plates in floor are collapsing in the machining areas. | Life & Safety Issue | 25000 | OSHA requirement | Proposals for Design engineers to prepare construction documents are currently being created. Once Architect/Engineer is selected next steps: Board approval, Contract Document preparation, DSA review and approval Bidding, then Construction. • Gary Banks, Fac. Project Manager, to investigate.
1 | 2 | IN-PROGRESS Design Engineer Selection | Laney | Central Plant | R | Chillers are undersized for required air volume needed. Boiler should be upgraded. | Life & Safety Issue | 80000 | The seasonal high temperature for the area surrounding Laney is 79 degrees. | Proposals for Design engineers to prepare construction documents are currently being created. Once the Architect/Engineer is selected. Next steps will be: Board approval, Contract Document preparation, DSA review and approval Bidding, then Construction.
5 | 2 | IN-PROGRESS Project Development | Laney | "A" Building air handlers | R | Negative air pressure | Life & Safety Issue | 200000 | No comment | Existing HVAC units are beginning to fail due to age. Project is being created to replace units.
6 | 2 | IN-PROGRESS Project Development | Laney | Upper "G" building | R | Negative air pressure in Architecture Department. Problems with makeup air system. | Life & Safety Issue | 200000 | No comment | Existing HVAC units are beginning to fail due to age. Project is being created to replace units.
7 | 2 | IN-PROGRESS Design Engineer Selection | Laney | Pneumatic controls across campus Air tube leaking | R | Pneumatic system is literally crumbling and should be replaced. No local control of heating. An upper A classroom will be cold, request higher temperature and a lower A classroom becomes too hot. | Life & Safety Laney - Comment: This work could be partially funded from Prop 39 tied to energy savings | 100000 | No comment | Proposals for Design engineers to prepare construction documents are currently being created. Once the Architect/Engineer is selected. Next steps will be: Board approval, Contract Document preparation, DSA review and approval Bidding, then Construction.
2 | 2 | IN-PROGRESS Design Engineer Selection | Laney | Gas infrastructure across campus | R | Gas infrastructure should be thoroughly checked and upgraded as needed. | Life & Safety Issue | 700000 | No comment | Proposals for Design engineers to prepare construction documents are currently being created. Once the Architect/Engineer is selected. Next steps will be: Board approval, Contract Document preparation, DSA review and approval Bidding, then Construction.
NR in progress--no ranking needed per VC General Services | 2 | IN-PROGRESS Design Engineer Selection | Laney | Campus wide | R | For documentation of many of these structural issues talk to Jeff Cook. As manager of the ADA project at Laney he had to initiate numerous change orders to fix broken pipes , drains and other structural problems when walls or grounds were opened up to accomplish the ADA work | Life & Safety Issue | 20000 | No comment | Proposals for Design engineers to prepare construction documents are currently being created. Once Architect/Engineer is selected next steps: Board approval, Contract Document preparation, DSA review and approval Bidding, then Construction. • May be resolved when Breezeway Project is completed.
3 | 2 | IN-PROGRESS Design Engineer Selection | Laney | Electrical infrastructure across campus | R | Electrical system is aging and should be replaced. . | Life & Safety Issue | 500000 | No comment | Proposals for Design engineers to prepare construction documents are currently being created. Once the Architect/Engineer is selected. Next steps will be: Board approval, Contract Document preparation, DSA review and approval Bidding, then Construction. Transformer plus switch gear.
C | C | Completed | Laney | Men's restroom, eagle village | R | Hole has opened up in floor of men's restroom. Serious trip hazard. Repair needed. | Life & Safety Issue | 15000 |  | COMPLETED
C | C | Completed | Laney | Biology Lab B204 & Microbiology Labs B203 | M | Fire extinguishers missing from B204 (prep area) and B203 microbiology lab. |  | 300 |  | COMPLETED
C | C | Completed | Laney | Biology Lab, B210 | R | Light switches in B210 often do not operate. | When the switch by the main door does not work, instructors must walk across the room in the dark to the other set of switches, which function better but are still unreliable. | 1000 |  | COMPLETED
C | C | Completed | Laney | Biology Lab | R | Leaking faucets in labs | Potential hazard as leaking faucets are near electrical outlets and equipment. | 100 |  | COMPLETED
C | C | Completed | Laney | Chemistry Lab - A277, A278, & A279. | M | Signage needs to be reinstalled near eyewash/chemical shower stations | Life & Safety Issues | 250 |  | COMPLETED
C | C | Completed | Laney | Chemistry Labs - A235,A236, A235A, A237, A277, A278 & A279 | R | Fix eyewash station drain vents | Life & Safety Issues. Sewer vapors enter laboratory in A236 – but all floor mounted stations in have same style drain. | 100 |  | COMPLETED
C | C | Completed | Laney | A152 | R | Sewer gasses escaping from floor drains in old platemaking and darkroom areas. | Life & Safety Issue | 25000 |  | COMPLETED
[6 empty] | LANEY TOTALS: |  | 3378250

## MERRITT
Ranked by Order of Priority (1st, 2nd, 3rd, etc)
2013-10-22
MERRITT COLLEGE
COLLEGE RANKING | RISK MANAGEMENT RANKING | STATUS | College | Building /Area | M= Maint. R = Repair | Description | Justification / Comments | ENGINEERING COST ESTIMATES | RISK MANAGEMENT Comments | DGS Comments
1 | 1 | IN-PROGRESS Project Development | Merritt | Pathway E & D | R M | Major tripping hazard | Broken/heaved sidewalk | 9000 | Until repairs can be completed identify hazard with yellow hazard warning paint | Cost Proposals have been solicited and Project being created. Cost proposals due the week of September 20, 2013. Work to begin as soon as contract is approved. $9,000 - Concrete replacement.
2 | 1 | IN-PROGRESS Construction Documents | Merritt | E & D Entrance | R M | Stairs are deteriorating | Repair / remove wood stair lip | 75000 | Until repairs can be completed identify hazard with Warning Signs and yellow hazard warning paint | Proposals for Design engineers to prepare construction documents are currently being created. Once Architect/Engineer is selected next steps: Board approval, Contract Document preparation, DSA review and approval Bidding, then Construction.
3 | 1 | CUSTODIAN TO REPLACE BULBS | Merritt | A Exterior | R | Exterior lights not working properly | replace bulbs | 1000 | Require Business Office to prioritize replacement of bulbs as Priority 1 | This task is typically performed by the Campus Custodians. Maintenance will assist as necessary.
4 | 1 | IN- PROGRESS PRIORITY | Merritt | E lot | M | New Face Plate | Safety Risk Requires pulling fiber, VoIP | 30000 | Safety risk | Maintenance - In Process Assigned High Priority 44 - Non-Functional (District-wide) 18 - Functional
5 | 1 | IN - PROGRESS Bid Development | Merritt | G lot | R | Ruts and speed bumps no paint | Access for all users of the fields | 15000 | Recommend temporary asphalt patching until permanent correction can be scoped and repairs funded and completed repairs Pricing is done. | Scope being developed to go out to bid for resurfacing Parking Lots B and G. Pricing is done.
6 | 1 | IN- PROGRESS PRIORITY | Merritt | Q third floor | R | President's office doors does not secure | President works late | 3000 | Locking doors required to protect staff security and safety; Required to protect confidential information | Maintenance - In Process Assigned High Priority. Communications to phone iciness in-progress. • Kirk Schuler, Chief Stationary Engineer to follow-up
7 | 1 | IN- PROGRESS PRIORITY | Merritt | Child Care |  | Door buzzer for entry to childcare facility do not work | To prevent unauthorized entry | 150 | Necessary to ensure child security and safety | Maintenance - In Process Assigned High Priority • Kirk Schueler, Chief Stationary Engineer to follow-up.
8 | 2 | IN-PROGRESS Project Development | Merritt | Gym Showers | R | No hot water for showers | adapt to on demand hot water | 75000 | No comment | Initial investigation indicated problems with Boilers and existing piping. Project being created to obtain design engineer, prepare scope and bid out for construction repairs. Hot Water heat exchange not connected. RFP estimated cost is for Design Engineer only. Total project cost is estimated at over $1 million.
City | 3 | CITY OF OAKLAND JOB | Merritt | B lot | M | No arterial from parking to main | Work with City planning | 30000 |  | Request letter being drafted for City of Oakland.
C | C | Complete | Merritt | R,Q, D, A & F | R M | Elevators not working | State compliance | 20000 |  | COMPLETED
[6 empty] | MERRITT TOTALS: |  | 258150